## Slide 1
Closing the Upstream Blind Spot
A Proposal to Extend Tool Readiness Tracking
into Facility & Pre-Hookup Dependencies
Executive Briefing | PPP Cycle 2026

## Slide 2
THE PROBLEM
We Can Measure the Bleeding — But Not the Wound
WHAT WE HAVE
On-Time Ready for
In-Service %
A working prototype that
tracks the outcome — but only
the outcome.
WHAT WE DON'T HAVE
Facility pre-hookup progress
Gas-line & utility readiness
Vendor package delivery status
Site assessment sign-off tracking
Design review completion
When leadership asks "why are we missing target?" — we cannot answer.

## Slide 3
IMPACT
Anatomy of a Missed Readiness Date
A typical delayed tool — reconstructed after the fact
Facility Mod
+3 wks late
Gas Hookup
+2 wks late
Vendor Pkg
Incomplete
Install
On time
Qual & IS
Delayed 6 wks
WHEN WE FOUND OUT
At tool move-in. Crew arrived to discover facility mods incomplete, gas lines not started, vendor documentation missing. Scrambled to investigate — 2-week manual post-mortem.
WHEN WE COULD HAVE KNOWN
6 weeks before move-in. With upstream tracking, facility delay flagged automatically. Escalation triggered. Two of three issues recovered before tool arrival. Readiness met.
THE GAP BETWEEN THESE TWO ROWS IS THE ENTIRE VALUE OF THIS PROJECT

## Slide 4
INDUSTRY CONTEXT
This Is Not a New Idea — Leaders Are Already Investing
Deloitte ELM
Cloud-based control tower tracking thousands of equipment components from supplier to fab, flagging delays in real time.
Equipment Lifecycle Mgmt
Bechtel + Intel
Data mesh architecture on Intel's Ohio fab for real-time synchronization across all construction systems. Projecting up to 40% schedule gains.
Integrated Data Visibility
TSMC + NVIDIA
Digital twin of new fabs to proactively identify equipment collisions, system interdependencies, and KPI impacts before build.
Proactive Dependency Mgmt
ABM-WGNSTAR
Integrated facility-tool readiness model eliminating handoff delays
Oil & Gas
Stage-gate readiness checks standard for capital projects since 2000s
Bosch / Intel
Digital twins for fab operations, renovation planning without disruption

## Slide 5
THE SOLUTION
Extending What We Have Into the Upstream Blind Spot
Three phases. Each delivers standalone value. Phase 1 is the ask.
1
TRACK
Upstream Dependency Tracking
Pre-hookup progress by component | Facility readiness milestones | Stoplight view per tool
Q1–Q2 2026
2
GOVERN
Sign-Off Workflows & Alerts
Gate sign-offs with timestamps | Missed-timeline alerts | Accountability trail
Q3 2026
3
PREDICT
Analytics & Root Cause
Drill-down from readiness % | Delay root cause categories | Predictive risk scoring
Q4 2026+
Phase 1 alone turns the readiness KPI from a rearview mirror into a windshield.

## Slide 6
DECISION-MAKING IMPACT
From Reactive Post-Mortems to Proactive Recovery
TODAY
1
1
Readiness number drops below target
2
2
Leadership asks: "Why?"
3
3
Manual investigation — chasing emails, calling sites
4
4
2-week post-mortem produces findings
5
5
Findings arrive too late to affect the next cycle
WITH UPSTREAM TRACKING
1
System flags 3 tools at risk — 6 weeks early
2
Facility pre-hookup behind on 2 tools
3
Auto-escalation to facility & vendor teams
4
Two of three recovered before move-in
5
Root cause data feeds next cycle improvements
The difference: problems found at move-in vs. problems prevented 6 weeks before.

## Slide 7
SUCCESS METRICS
Proposed KPIs & Measurable Outcomes
On-Time
Readiness %
Improve by
X → Y%
Primary KPI — baseline in Phase 1, improve in Phase 2
Mean Time
to Detect
Reduce from
Move-in → 6 wks early
How early we identify at-risk tools upstream
Root Cause
Resolution
From manual to
Automated
Categorized delay drivers by type within 24 hours
Idle Capital
Days
Reduce by
TBD per tool
Dollar value of each day saved on floor idle time
Note: Exact baseline targets to be established in Phase 1 pilot. Insert your current readiness % here.

## Slide 8
THE ASK
Phase 1 Pilot — Bounded, Low-Risk, High-Signal
Scope
Pre-hookup dependency tracking for one tool type at one site for one quarter
Team
1 project lead (full-time)
1 data architect (part-time)
Facilities team cooperation
Duration
12 weeks to deliver
tracking infrastructure
and run pilot
Outcome
Measurable: did upstream visibility improve on-time readiness for pilot tools?
We already invested in measuring the outcome.
Now we need to measure the inputs.

## Slide 9
APPENDIX
The Full Dependency Chain — From PO to In-Service
Tool
Purchase
→
Vendor
Design Pkg
→
Site
Assessment
→
Facility
Mod
→
Pre-
Hookup
→
Tool
Move-In
→
Hook-Up
& Install
→
Qual
→
In-
Service
NO SYSTEM TRACKS THIS — THE BLIND SPOT
MEASURED TODAY
The red zone represents all upstream dependencies that must complete before your team touches the tool — and currently have zero systematic tracking. The project proposes to close this gap, starting with facility pre-hookup and expanding to the full upstream chain.
Questions This System Will Answer:
Is the facility mod on track for Tool X's move-in date?
Which tools are at risk of missing readiness this quarter?
What % of delays originate from facilities vs. vendors vs. internal?
Where should we focus resources to recover the most tools?